## Sheet1
team 4 - food bank project tasks
Task | Who | Due | Status | notes | done?
--- setup stuff ---
team charter | Sofia | 9/3 | done | priya submitted fri | x
email dana re kickoff | Ty | wk 3 | done |  | x
kickoff questions | Kwame | 2026-09-08 | done
--- PROPOSAL ---
problem statement/background | sofia | 9/19 | done |  | x
scope + deliverables | Priya | 9/19 | Done!!
tech approach | jordan | 9/19 | done |  | x
timeline | PR | 9/19 | done
get scope agreement signed | Tyler B. | 9/24 | done | in drive? | x
submit proposal | Priya | Sept 25 | done |  | x
--- research report ---
interviews (8) | Kwame | 10/5 | done | 6 vol + 2 coord | x
user interview synthesis | Kwame | 10/7 | in progress
personas | Kwame/Mei | 10/7 | done |  | x
requirements list | Sofia | 10/7 | done |  | x
get Dana's current signup spreadsheet | Tyler | ?
competitive review |  |  | done | mei did most of it
submit report | priya | 2026-10-09 | done |  | x
--- PROTOTYPE (M3) due 10/30!!! ---
build app in react | Jordan | wk 10 | in progress | repo set up
volunteer screens | Mei | 10/16 | done
coordinator screens | Mei | 10/20 | wip
link flows in figma | jordan | before demo | in progress | signup + reminder done
accessibility check | Kwame |  | not started | after screens done
WCAG review | Mei? | 10/27
traceability matrix | Sofia | 2026-10-23 | in progress
schedule demo w/ Dana | Ty | ASAP | in progress
privacy plan | ? | 10/30?
peer evals | everyone | nov 6?
submit M3 | priya | 10/30
ask dr okafor about the late policy??