# Team 4 Meeting Notes - Week 8

Date: Tue Oct 13, 2026, 6:00-7:20pm (Zoom)

Present: Priya, Jordan, Mei, Sofia, Kwame. Absent: Tyler (family stuff, messaged ahead)

Notes by: Priya

## Recap

- Milestone 2 (research & requirements report) submitted Fri 10/9.

- Mei redid all 9 volunteer screens in Figma over the weekend based on what came out of Kwame's interviews (bigger text, fewer steps to sign up, text reminders instead of email). Huge, thanks Mei. Coordinator screens (5) are next.

## Milestone 3: prototype + sponsor demo, due Fri Oct 30

Went through the rubric together. Big pieces: working prototype of the 3 core flows (35%), traceability (15%), accessibility review (15%), sponsor demo + feedback notes (15%), data & privacy plan (10%), updated project plan (10%).

## Decisions

- DECISION: For M3 we are doing a clickable Figma prototype, not coded. Jordan wanted to keep going in React but agreed it is not realistic by 10/30 with his work schedule. React can come back for the final if we have time.

- DECISION: Jordan links Mei's screens into clickable flows in Figma (sign up for shift, get reminder, coordinator roster).

- DECISION: Kwame does the accessibility review (WCAG checklist) once Mei's screens are final.

- DECISION: Sofia does the traceability matrix (features vs. requirements from M2).

## Open / not decided

- Data & privacy plan: nobody has it yet. Maybe Tyler since he has been talking to Dana about what info they collect? Need to ask him.

- Sponsor demo needs to be booked with Dana. Tyler is the liaison. I will text him to make sure he knows about the 7-day rule.

## Action items

- Mei: volunteer screens final by Fri 10/16, coordinator screens by Tue 10/20

- Jordan: start linking the volunteer flows this week

- Sofia: traceability matrix draft by Fri 10/23

- Kwame: accessibility checklist, start once screens are done

- Priya: text Tyler re: demo + privacy plan