Team 4 - Weekly Meeting, Week 6

Tuesday Sept 29, 6:05pm. Notes: Kwame. Present: Priya, Jordan, Mei, Sofia, Kwame. Tyler messaged that he was sick.

1) Proposal

Submitted 9/25. Tyler said in the chat that Dana signed the scope agreement and it's in the drive.

2) Research report (due Fri Oct 9)

- Interviews: I have done 3 so far (2 volunteers, 1 coordinator). Goal is 8 total, 6 volunteers + 2 coordinators. Dana is helping recruit.

- Personas: Mei + me

- Requirements list: Sofia

- Competitive review: Mei already did most of this (SignUpGenius, VolunteerHub, Sign Up Zone). Sofia will fold it into the report.

3) Tech

Jordan set up a React starter project on GitHub. Priya asked him to keep it small until requirements are done.

4) Peer evals

Dr. Okafor reminded the class that the first peer evaluation is due with Milestone 3.

Action items

- Kwame: finish remaining 5 interviews by Mon 10/5

- Kwame + Mei: 2-3 personas by Wed 10/7

- Sofia: requirements list draft Wed 10/7, full report put together Thu 10/8

- Tyler: ask if Dana can share their current sign-up spreadsheet (for requirements)

- Priya: final read + submit Fri 10/9